## Cover
BILLS OF QUANTITIES
FOR
PROPOSED REFURBISHMENT AND EXTENSION OF OPERATING THEATRE
AT
KAKUMA MISSION HOSPITAL
FOR
MALTESER INTERNATIONAL
BILLS OF QUANTITIES
| ARCHITECTS |  | QUANTITY SURVEYORS
| ARTISAN ARCHITECTS LTD |  | METICULAR CONSULTANTS LTD
| P.O. Box24680-00100 |  | P.O. Box 1524-00100
| Nairobi, Kenya. |  | Nairobi, Kenya.
| Email:info@artisan.co.ke |  | Email: info@meticular.co.ke
(vi)
SEPTEMBER, 2026

## Form of Tender
FORM OF TENDER
FOR
PROPOSED REFURBISHMENT AND EXTENSION OF OPERATING THEATRE
AT
KAKUMA MISSION HOSPITAL
FOR
MALTESER INTERNATIONAL
To:
Sirs,
|  | 1. | I / We .................................................................................................. (name) under and subject to the Conditions of Tendering hereby Tender and offer to execute and perform the works and provisions and supply all labour and materials and everything of the kind respectively named, shown, described and alluded to in, or to be inferred from the form of Contract Agreement, the General Conditions of Contract, Bills of Quantities and Drawings to be executed and supplied on the part of the Contractor, for the works above described for the sum of:-
Kenya Shillings (in words) ..................................................................................…………………………
………………………………………………………………………………………….………..
………………………………………………………………………………………………………...
Naira………...................................................………… ………………………………………...............
|  | 2. | I / We agree to complete the works within ________ CALENDAR WEEKS from the date of possession of the site or within such extended time as the General Conditions of Contract provide.
|  | 3. | I / We further agree to be bound by and submit to the said General Conditions of Contract and priced Bills of Quantities which shall form a basis for the valuation of interim certificates and any extra or omitted work which may from time to time be ordered by the Architect.
FORM OF TENDER |  |  |  | FT/1
|  | 4. | If my / our tender is accepted, I / we will when required, provide a Bank, Insurance Company or Fidelity Guarantee Corporation Surety who will be willing to be bound to the Employer in the amount equal to 10% of the Contract Sum for the due performance of the Contract and who will, when and if called upon, sign a Bond to that effect.
NAME OF SURETY:
................................................................. .........………….............................. ....................
................................................................. ............................…………................................
|  | 5. | Whereas it is understood that you reserve to yourself the right to accept or to refuse this Tender, whether it be lower or higher than any other Tender or of the same amount, the undersigned agree that this Tender shall remain valid and shall not be withdrawn within ninety (90) days from the final date of the submission of the Tenders.
|  | 6. | Unless and until a formal Agreement is prepared and executed, this Tender together with your written acceptance thereof, shall constitute a binding contract.
|  | 7. | I / We acknowledge receipt of the following addenda to the Contract Documents (if none were received, write the word ‘none’).
|  |  | Addendum No. | Date of Addendum
|  |  | ……………………………. | …………………………….
|  |  | ……………………………. | …………………………….
|  |  | ……………………………. | …………………………….
|  |  | ……………………………. | …………………………….
|  | 8. | The following approved Sub-contractors who have priced for the specialist services, subject to the approval of the Architect, will be employed by the tenderer as domestic sub-contractors to execute their respective specialist work.
FORM OF TENDER |  |  |  | FT/2
Dated this .......................................... day of ..……………………...................2024
Signature:.......................................................…………………….......................……
Name of Firm:.................................................................……………………......……
......................................................................…………………………….
......................................................................…………………………….
BLOCK LETTERS
Address: ........................................................................……………………….............……
Telephone: .............................................……………………......................................…...
Witness’s Name: ............................…………………….................................................…..
Address: ...............................................................…………………….........................……
Occupation: .......................................................………………….............................…...
Date: ................................................. Telephone: ..….....................……………………..
BLOCK LETTERS
FORM OF TENDER |  |  |  | FT/3

## Surety Undertaking
SURETY UNDERTAKING
To:
We……………………………………………………………………………………of (Address) …………………………..………………………………………(Surety)
Are willing to act as Surety and to be bound to MALTESER INTERNATIONAL, in the sum equal to Ten Percent (10%) of the Contract Amount for the due performance by
……………………………………………………………………………………………………
………………………………………………………………………………………………
……………………………………………………………………... (Tenderer) of (Address)
………………………………………………………………………………………………….
for a Contract which he/they contemplate(s) entering into for Construction of the PROPOSED REFURBISHMENT AND EXTENSION OF OPERATING THEATRE to the terms and Conditions of Contract, a copy of which has been inspected by us, without the addition of any limitation. We agree to enter into a Bond under the above terms within seven days of being called upon to do so.
……...………………………………….……………………………………………. (Surety)
Date ……………….…………..……………………………………………………..
Witness ……………………………………………………………….……………..
……………………………………………………………….……………..
……………………………………………………………….……………..
……………………………………………………………….……………..
SURETY UNDERTAKING |  | SU/1

## Pricing Notes
PREAMBLE AND PRICING NOTES
PROPOSED REFURBISHMENTS AND EXTENSION OF OPERATING THEATRE AT KAKUMA MISSION HOSPITAL
Introduction
These price notes form part of the Bills of Quantities.
The Permanent Works shall be measured notwithstanding any general or local custom except where otherwise specifically described or prescribed in the Contract.
The rates and prices in the Bill of Quantities shall, except where otherwise provided in the Contract, cover all the Contractor's obligations under the Contract and all matters and things necessary for the proper execution and maintenance of the Works.
The items provided in the Bill of Quantities shall be the only items against which payment shall be made, except that where additional items are required in respect of authorized additional works, payments may be made against such additional items.
The Contractor shall be deemed to have included in his rates entered against the items in the Bill of Quantities for all activities necessary to complete the Contract Works, including any items of Work, which, in his opinion has been omitted from the Bill of Quantities.
Except where otherwise detailed in the Bill of Quantities or specified, labor, including the supervision thereof, materials, Constructional Plant, Temporary Works, transport to and from the Site and in and about the Works, laboratory testing and other things of every kind required for the execution and maintenance of the Works shall not be measured and the cost thereof shall be deemed to be included in the rates and prices in the Bill of Quantities.
The total quantity included in the final measurement of each item shall be measured to the nearest integer relative to that item, or to one decimal place if so indicated in the Bill of Quantities.
The following abbreviations are used in the Bill of Quantities:
LM:Shall mean Linear Meters
SM: Shall mean Square Meters
CM: Shall mean Cubic Meters
Kg: Shall mean Kilogram
M: Shall mean Meters
MM: Shall mean Millimeters
NO: Shall mean Number
Hr: Shall mean Hours
KM: Shall mean Kilometer
ha: Hectare
USD -US dollar
lin: Linear
min: Minimum
HP: Horse power
%: Shall mean Percentage
Dia: Shall mean Diameter
B.S: Shall mean the British Standards or British Standards Specifications published by British Standards Institution, 2 Park Street, London W.l.
Ditto: Shall mean the whole of the preceding description except as qualified in the section in which it occurs. Where it occurs in brackets, it shall mean the whole of the preceding description which is contained within the appropriate brackets
b.s.m: Shall mean both sides measured
m.s: Shall mean measured separately
n.e: Shall mean not exceeding
P.C: Shall mean Prime Cost
P.S: Shall mean Provisional Sum
Where in the Bill of Quantities there is a Schedule or subsidiary bill setting out the quantities of component materials and work which comprise a unit of work measured under a single item in a Part of the Bill of Quantities, the said quantities shall be subject to measurement and valued at the rates and prices entered therein and the total thereof shall be the rate for the item.
For items which the unit of work is given as “Sum” and the quantity of work is given as “Item”, otherwise than the items brought forward from a subsidiary schedule as explained above, the proportions of payments in interim payments shall be made, according to ratios based on the percentage of work or components of work completed and/or, in installments defined by the period covered by the interim certificate to the total period for which such works/facilities are provided. Such ratios and installments shall be determined by the Engineer. In his determination, the Engineer is at liberty to consider a breakdown of lump-sum items provided by the Contractor. At any stage during the duration of the Contract, the Engineer will be entitled to adjust such ratios and installments to correspond with any amendment to the duration of the works as related to completion of the Works.
Any item of work included in the Bill of Quantities for which no rate or price was specified shall be considered as included in other rates and prices in the Bill of Quantities and will not be paid for separately.
Definitive list of works is provided by the Bill of Quantities only and the quantities listed on the drawings and other tables are for information purposes only.
Provisional Quantities, Optional Works and Alternative Items
Provisional Quantities
Items in the Bill of Quantities for which the quantities are stated to be provisional shall only be executed if they are the subject of a written instruction from the Engineer. The rates set out for such items shall be used for the valuation of works so ordered by the Engineer in writing whether the quantities shown are used wholly or in part. If the amount of work ordered by the Engineer to be executed under a Provisional Quantity item exceeds the quantity shown in the Bill of Quantities, the rate for that item set out in the Contract shall be deemed applicable to the excess.
Schedule of Rates
General
The activities covered by the Schedule of Rates are general activities of a routine nature which are similar or the same as some of the activities which shall be paid for under other items in the Bill of Quantities.
The Contractor shall be deemed to have drawn on his technical expertise in entering the Prices and shall have made all due allowances for conforming to relevant codes, standard practice and the Specifications.
Anomalous Rates
The rates entered in the Schedule of Rates will be scrutinized as follows:
Where a rate is entered for an item in the Schedule of Rates and an equivalent item is provided under the Bill of Quantities, the rate in the Schedule of Rates should match the rate in the Bills of Quantities. Where such rates do not match; the lower rate for such similar items will govern.
Where a rate is entered for an item in the Schedule of Rates and there is no equivalent item provided under the Bills of Quantities, the bidder may be requested to provide a breakdown of the constituent costs of any rate together with the constituent costs of rates for specified items within the priced Bill of Quantities and demonstrate that the rate in the Schedule of Rates is priced in a manner consistent with the rates provided in the Bill of Quantities. In the event that the bidder cannot demonstrate such consistency, at the Employer discretion the rate in the Schedule of Rates shall be adjusted.
Optional Works
Items in the Bill of Quantities for which the quantities are stated to be optional shall only be executed if they are the subject of a written instruction from the Engineer.
Alternative Items
Alternative Items will not be considered in the evaluation of the bids. However, the Employer has the right to subsequently select the alternative item for implementation.
Day works
Provisional Sums for use when work is executed on a day work basis. Work shall not be executed as day work except by written order of the Engineer.
Labor
Payment in respect of labor employed on a day work basis shall be at the rate entered in the day work rates and no payment shall be made in respect of overtime. A work day is defined as an 8 hour working day including weekends and public holidays.
Construction Equipment
Payment in respect of Construction Equipment employed in the execution of the work on a day work basis, shall be at the rates entered in Day work Bill
The time for which Construction Equipment is broken down or during which it is being serviced shall not be measured, nor shall that of any labor or other Constructional Equipment which is unable to work by reason of such breakdown or servicing.
The rates for construction equipment working shall include for all operation and maintenance costs, fuel, oil, inclusive of drivers and attendants.
Plant and Materials
Payment in respect of plant and materials used in the execution of work on a day work basis shall be according to the rates of plant and materials entered in Bill 5, which shall include the cost of taking the plant and materials from the store or stockpile on the Site to the place where they are used.
General
No separate payment shall be made for complying with the provisions of the following Clauses of the Technical Specification except where explicitly provided in the Bill of Quantities.
Payment for diversion and/or modification of existing utility and road crossings of whatsoever kind shall be made under the items as set out in the Bill of Quantities for “temporary access roads” and for “temporary diversion works” as appropriate.
Where the unit of such work is defined as a “Sum” in the Bill of Quantities, the amount entered for that “Sum” shall be deemed to cover all components of work in order to complete the work. Components of such work, (e.g. removal of existing services, excavation, supply, laying and jointing of pipes, concrete, reinforcement, pile forming /driving, all temporary arrangements, etc.) shall not be separately measured.
No separate payment shall be made for the Contractor servicing any cranes and handling devices on completion of works that he has made use of during the works.
While determining unit rates, the Contractor shall take into consideration any site specific construction complexities and include their cost into the respective unit rates.
The Site
No separate payment shall be made for complying with any of the requirements of the Technical Specification with regard to the Contractor’s activities and requirements for the Site except as explicitly set out in the Bill of Quantities and where such items are provided these shall be deemed to cover all matters, costs and expenses.
The Contractor shall be deemed to have included in his rates for:
_ Organization of construction works when deriving his rates.
Temporary Works
Eighty percent (80%) of total lump sum price of temporary works will be paid to the Contractor upon completion of these temporary facilities, and the remaining twenty percent (20%) of the total price will be paid after handing over to the Employer of these temporary facilities.
Photographs
Payment for photographs as per the Employer’s requirements shall be deemed to be included in the Contractor’s rates if not stated as an extra item in the Bill of Quantities.
Control of Water
Payment for control of ground and surface water shall be deemed to be included in the Contractor’s rates if not stated as an extra item in the Bill of Quantities.
Materials and Workmanship
No separate payment will be made for complying with the provisions of Technical Specifications with respect to obtaining the specified standards and class of workmanship or complying with Standards ordered by the Engineer shall be paid at the net cost for supply of standards plus the percentage in the space provided for the relevant item.
Earthworks and foundations
No separate payment shall be made for complying with the provisions of earthworks except where explicitly provided, and no separate payment will be made for:
Fill / Backfill made by the Contractor for any purpose or reason, for over excavation or fill and for removal of material.
Payment for drainage pipes will be included in the Bill of Quantities. The payment will include all labor, equipment, tools and other incidentals for providing the slits and stops.
Special requirements for earthworks and foundation works at four (4) meter depth
No separate payment shall be made for complying with these requirements;
-Build the 4.0m foundation walls and cast columns in lifts not exceeding 1000mm.
-The mortar joints and column concrete shall be allowed to cure for at least 24 hours after which the column formwork shall be struck off.
-The wall surround shall then be backfilled simultaneously on both sides with suitable material upto a height of 900mm in layers not exceeding 150mm compacted to 98% MDD.
-This shall be repeated for the next three lifts.
Stripping
In case of separate Bill items for stripping, this will be measured for payment by the square meter and shall include a depth of 0.3 m below original ground surface. Quantities for payment will be computed by direct measurement of areas stripped, and will include only the locations directed by the Engineer. Payment will be made at the unit rates per square meter tendered therefore in the Bill of Quantities.
Clearing and Grubbing
Clearing and Grubbing shall be measured in square meters and payment will be made at the unit rates per square meter tendered therefore in the Bill of Quantities.
Site Investigations
Measurement and payment for site investigations where ordered by the Engineer shall be made on day-work report basis.
No separate payment shall be made for site investigations which are an integral part of the Contractor’s general activities under the Contract.
Clearance Works
Rates for removal of any type of existing structures and buildings (reinforced concrete, steelwork, etc.), their contents or general waste materials (including municipal waste) shall be included in the Contractor’s rates and prices except where it is expressly measured by a lump sum amount, or by volume as provided for in the Bill of Quantities.
The rate in the Bill of Quantities shall include all work necessary for the removal, transportation and safe disposal of materials in accordance with the Technical Specification.
Concrete
The unit rate for concrete works shall cover all costs that are necessary to obtain the concrete quality including, but not limited to the following items:
_ Delivery and storage of all materials
_ Preparation and submission of working drawings and calculations
_ all batching, mixing and transport equipment, including all required personnel and foremen
_ preparing, transporting and placing of concrete
_ finishing of surfaces
_ making and curing of test cubes, including laboratory tests;
_ curing of concrete, including materials and equipment;
_ drilling and cutting of concrete cores, including equipment and testing;
_ transportation, keeping on the site, including loading and unloading.
Shuttering
Shuttering shall be measured and paid for separately under the Bill of Quantities. No extra payment for cooling or soaking shuttering shall be made.
Reinforcement
Unless otherwise stated in the Bills of Quantities no separate payment shall be made for reinforcement.
Where the item for concrete in the Bills of Quantities refers to a quantity or rate of reinforcement in the concrete, no separate measurement shall be made for reinforcement.
In such cases the concrete rates in the Bill of Quantities shall be deemed to include for reinforcement at the minimum of the density stated.
Where the Bills of Quantities provide for measurement of steel reinforcement bars, the weight shall be calculated on the basis of the relevant Technical Specification.
The rates for steel reinforcement, whether explicit or implicit, shall include all expenditures incurred in providing, cutting, bending, placing and fixing the reinforcement in its final position in the structure.
Finishes
Finishes shall not be subject to additional payment and shall be deemed to be included in the rates for concrete.
Miscellaneous
No separate payment shall be made, for supply and testing of concrete ingredients; storage of materials; determination of mix proportions; making and testing of trial mixes; testing of concrete; control and mixing of concrete; transporting, placing and compacting concrete; finishes; construction joints (whether shown on the Drawings or not except that where a water stop is specified or ordered by the Engineer to be incorporated in construction joints it shall be measured by length for each type and size required); molds for transporting and fixing precast work; precautions for concreting in unfavorable weather; curing; ascertaining requirements for reinforcement, bending, cutting and fixing reinforcement or working space for erection and handling of shuttering.
If the Engineer so directs, samples of cement, water and fine and coarse aggregates shall be delivered by the Contractor to the Engineer for independent testing; such testing shall be charged directly to the contractor.
Removal of concrete structures
Demolition works to concrete structures shall be measured net as volume.
No separate payment shall be made for disposal of debris and waste in accordance with the Specification or for making good any damage arising from retained elements.
Precast Concrete Structures
Precast concrete and reinforced concrete will be measured in cubic meters or in case of pipes and manhole rings per unit or length as stated in the Bill items.
The unit rates for reinforced concrete elements must cover all costs, the following items inclusive:
_ Submission of working drawings;
_ Delivery and storage of all materials;
_ All equipment, including devices for dosing, mixing and transportation, and operating personnel;
_ Preparing, transporting and placing of the concrete;
_ Finishing of surfaces;
_ Making and curing of test cubes, including laboratory tests;
_ Curing of concrete, including material and equipment;
_ Transportation and storage of prefabricated elements at the site
The rates for precast reinforced concrete pipes and box units shall be deemed to include for supply and laying, including all joints and connections, except where the Bills of Quantities specifically provide for otherwise.
Rubble Walling
Placing of rubble concrete shall be measured by square meters stating the thickness.
Masonry
Stone masonry shall be measured in square meters complete and shall include for all preparation, materials and finishing, including all pointing
Painting
Unless otherwise provided for in the Bill of Quantities no separate measurement shall be made for complying with the requirements of the Technical Specification, the cost of which shall be included in the rates and prices relative to the items concerned.
Where items are provided in the Bill of Quantities for painting, it shall be measured as the surface area covered for the top coat only.

## Preliminaries
Item | Description | AMOUNT
BILL NO.1 PARTICULAR PRELIMINARIES
1 | PRICING OF ITEMS OF PRELIMINARIES AND PREAMBLES
Prices will be inserted against items of Preliminaries in the Contractor's priced Bills of Quantities and Specification.
The Contractor shall be deemed to have included in his prices or rates for the various items in the Bills of Quantities or Specification for all costs involved in complying with all the requirements for the proper execution of the whole of the works in the Contract.
2 | ABBREVIATIONS
Throughout these Bills, units of measurement and terms are abbreviated and shall be interpreted as follows:-
C.M. Shall mean cubic metre
S.M. Shall mean square metre
L.M. Shall mean linear metre MM Shall mean Millimetre Kg. Shall mean Kilogramme No. Shall mean Number
NO. Shall mean Numbers
B.S. Shall mean the British Standard Specification Published by the British
Ditto Shall mean the whole of the preceding description except as qualified in the description in which it occurs.
m/s Shall mean measured separately.
a.b.d Shall mean as before described. Km Shall mean Kilometre
Fix Only:- "Fix Only" shall mean take delivery at nearest railway station (Unless otherwise stated), pay all demurrage charges, load and transport to site where necessary, unload, store, unpack, assemble as necessary, distribute to position, hoist and fix only.
3 | EMPLOYER
The term "Employer" and "MALTESER INTERNATIONAL" wherever used in the contract document shall be synonymous.
4 | ARCHITECT The term "Architect" shall be deemed to mean: Artisan Architects, P.O BOX 24680-00100, NAIROBI
5 | QUANTITY SURVEYOR The term "Quantity Surveyor" shall be deemed to mean: Meticular Consultants Ltd of P.O BOX 1524-00100, NAIROBI
6 | ELECTRICAL ENGINEER
The term "Electrical Engineer" shall be deemed to mean
7 | MECHANICAL ENGINEER
The term "Mechanical Engineer" shall be deemed to mean
8 | STRUCTURAL ENGINEER
The term "Structural Engineer" shall be deemed to mean
9 | FORM OF CONTRACT
The Form of Contract shall be as stipulated in the World Bank Standard Bidding Document for Procurement of Small Works.
10 | PERFORMANCE BOND.
The Contractor shall find and submit on the Form of Bid an approved Bank and who will be willing to be bound the by Mercycorps in and amount equal to Ten per cent (10%) of the Contract amount for the due performances of the Contract up to the date of completion as certified by the Architect and who will when and if called upon, sign a Bond to that effect on the relevant standard form included herein. (without the addition of any limitations) on the same day as the Contract Agreement is signed, by the Government, the Contractor shall furnish within seven days another Surety to the approval of the Government.
11 | MEASUREMENTS
In the event of any discrepancies arising between the Bills of Quantities and the actual works, the site measurements shall generally take precedence. However, such discrepancies between any contract documents shall immediately be referred to the Architect. The discrepancies shall then be treated as a variation and be dealt with in accordance with Clause 43 of the said Conditions.
12 | LOCATION OF SITE
The site islocated at KAKUMA MISSION HOSPITAL
The Contractor is advised to visit the site, to familiarize with its nature as no claims arising from the Contractor’s failure to do so will be entertained.
The works to be carried out under this contract involve; Extension and Refurbishments of operating theatre OT at Kakuma mission hospital .
13 | CLEARING AWAY
The Contractor shall remove all temporary works, rubbish, debris and surplus materials from the site as they accumulate and upon completion of the works, remove and clear away all plant, equipment, rubbish, unused materials and stains and leave in a clean and tidy state to the reasonable satisfaction of the Architect. The whole of the works shall be delivered up clean, complete and in perfect condition in every respect to the satisfaction of the Architect.
14 | CLAIMS
It shall be a condition of this contract that upon it becoming reasonably apparent to the Contractor that he has incurred losses and/or expenses due to any of the contract conditions, or by any other reason whatsoever, he shall present such claim or intent to claim notice to the Architect within the contract period. No claims shall be entertained upon the expiry of the said contract period.
15 | PAYMENTS
As specified in Particular conditions of contract
16 | PREVENTION OF ACCIDENT, DAMAGE OR LOSS
The Contractor is notified that these works are to be carried out on a restricted site where the client is going on with other normal activities. The Contractor is instructed to take reasonable care in the execution of the works as to prevent accidents, damage or loss and disruption of normal activities being carried out by the Client. The Contractor shall allow in his rates any expense he deems necessary by taking such care within the site.
17 | BID SECURITY
Two Hundred Thousand Kenya Shillings.
18 | WORKING CONDITIONS
The Contractor shall allow in his bid for any interference that he may encounter in the course of execution of the works for the Client may in some cases ask the Contractor not to proceed with the works until some activities within the site are completed, as the facility will be operating as usual during the course of the contract.
19 | SIGNBOARD
Allow for providing, erecting, maintaining throughout the course of the Contract and afterwards clearing away signboard as designed, specified and approved by the Architect.
20 | LABOUR CAMPS
The Contractor shall NOT be allowed to house labour on site. Allow for transporting workers to and from the site during the tenure of the contract.
21 | MATERIALS FROM DEMOLITIONS
Any materials arising from demolitions and not re-used shall become the property of the Contractor. The Contractor shall therefore allow in his pricing credit for the salvage value of the materials including the cost of transporting them away from site as they accummulate.
22 | PRICING RATES
The tenderer shall include for all costs in executing the whole of the works, including transport, replacing damaged items, fixing, all to comply with the said Conditions of Contract.
23 | URGENCY OF THE WORKS
The Contractor is notified that these “works are urgent” and should be completed within the period stated in these Particular Preliminaries.The Contractor shall allow in this tender for any costs he deems that he/she may incur by having to complete the works within the stipulated contract
24 | PAYMENT FOR MATERIALS ON SITE
All materials for incorporation in the works must be stored on site before payment is effected, unless specifically exempted by the Architect. This is to include materials of the Contractor, nominated sub-Contractors and nominated suppliers.
25 | EXISTING SERVICES
Prior to the commencement of any work, the Contractor is to ascertain from the relevant authority the exact position, depth and level of all existing services in the area and he/she shall make whatever provisions which may be required by the authorities concerned for the support, maintenance and protection of such services.
26 | DELIVERY OF BID
Bids and all documents in connection therewith must be delivered in the addressed envelope which should be properly sealed and deposited at the offices as specified in the letter accompanying these documents or as indicated in the advertisement. Bids will be opened at the time specified in the letter accompanying these Bidding Documents or as indicated in the advertisement notice. Bid delivered/received later than the above time will not be opened.
27 | VALUE ADDED TAX
The Contractor’s attention is drawn to the Legal Notice in the Finance Act part 3 Section 21(b) operative from 1st September, 1993 and any ammendments thereof which requires payment of VAT on all contracts.
The tenderer is advised that in accordance with Government public notice
No. 35 & 36 Dated 11th September 2003 operational from 1st October 2003, withholding VAT will be levied against the contract sum by the Employer . The contractor should therefore include VAT in the rates.
28 | CURRENT WORKLOAD
It will be a condition of this tender that every tenderer declares his/her Litigation history, and provides a list of his/her ongoing projects indicating the contract sum/tender amount, date of completion, current physical status and the value of the uncompleted works. Where there is no ongoing project, a Nil return must be made.
The list which must be submitted at the time of tender opening, shall cover project both with the Government and Public/Private sector bodies, being undertaken by the tenderer or about to commence.
Failure to fulfill this condition shall render the tender non-responsive.
PARTICULARS OF INSERTIONS TO BE MADE IN APPENDIX TO CONTRACT AGREEMENT
The following are the insertions to be made in the appendix to the Contract Agreement
A | The following are the insertions to be made in the appendix to the Contract Period of Final Measurement 3 Months From Practical completion Defects Liability Period 6 Months from Practical completion Date for Possession To be agreed with the Architect Date for Completion 52 Weeks from date of Possession
Period of Final Measurement: 3 Months From Practical completion
Defects Liability Period: 6 Months from Practical completion
Date for Possession: To be agreed with the Architect
Date for Completion: 52 Weeks from date of Possession
Liquidated and Ascertained : At the rate of Kshs.. 20,000…per week or part thereof
Period of Interim Certificates: Monthly
Period of Honouring Certificates 30 days
Percentage of Certified Value Retained 10%
Limit of Retention 10%
BILL NO.2 GENERAL PRELIMINARIES
A | PRICING OF ITEMS OF PRELIMINARIES AND PREAMBLES
Prices will be inserted against items of Preliminaries in the Contractor's priced Bills of Quantities and Specification.
The Contractor shall be deemed to have included in his prices or rates for the various items in the Bills of Quantities or Specification for all costs involved in complying with all the requirements for the proper execution of the whole of the works in the Contract.
B | PLANT, TOOLS AND VEHICLES
Allow for providing all scaffolding, plant, tools and vehicles required for the worksexcept in so far as may be stated otherwise herein and except for such items specifically and only required for the use of nominated Sub-Contractors as described herein. No timber used for scaffolding, formwork or temporary works of any kind shall be used afterwards in the permanent work.
C | TRANSPORT.
Allow for transport of workmen, materials, etc., to and from the site at such hours and by such routes as may be permitted by the competent authorities.
D | MATERIALS AND WORKMANSHIP.
All materials and workmanship used in the execution of the work shall be of the best quality and description unless otherwise stated. The Contractor shall order all materialsto be obtained from overseas immediately after the Contract is signed and shall also order materials to be obtained from local sources as early as necessary to ensure that they are onsite when required for use in the works. The Bills of Quantities shall not be used for the purpose of ordering materials.
E | SIGN FOR MATERIALS SUPPLIED.
The Contractor will be required to sign a receipt for all articles and materials supplied by the Architect at the time of taking deliver thereof, as having received them in good order and condition, and will thereafter be responsible for any loss or damage and for replacements of any such loss or damage with articles and/or materials which will be supplied by the Architect at the current market prices including Customs Duty and V.A.T., all at the Contractor's own cost and expense, to the satisfaction of the PROJECT
F | STORAGE OF MATERIALS
The Contractor shall make at his own risk and cost arrangement for storage of
materials for incoperation into the works. Nominated Sub-contractors are to be made liable for the cost of any storage accommodation provided specifically for their use.
The Contractor shall furnish at his own cost any samples of materials or workmanship including concrete test cubes required for the works that may be called for by the Architect for his approval until such samples are approved by the Architect and the Architect, may reject any materials or workmanship not in his opinion to be up to approved samples. The Architect shall arrange for the testing of such materials as he may at his discretion deem desirable, but the testing shall be made at the expense of the Contractor and not at the expense of the Architect. The Contractor shall pay for the testing in accordance with the current scale of testing charges laid down by the Directorate of Public Works.
The procedure for submitting samples of materials for testing and the method of marking for identification shall be as laid down by the Architect The Contractor shall allow in his tender for such samples and tests except those in connection with nominated sub-contractors' work.
G | GOVERNMENT ACTS REGARDING WORKPEOPLE ETC.
Allow for complying with all Government Acts, Orders and Regulations in connection with the employment of Labour and other matters related to the execution of the works. In particular the Contractor's attention is drawn to the provisions of the Factory Act 1950 and his tender must include for all costs arising or resulting from compliance with any Act, Order or Regulation relating to Insurances, pensions and holidays for workpeople or so the safety, health and welfare of the workpeople. The Contractor must make himself fully acquainted with current Acts and Regulations,including Police Regulations regarding the movement, housing, security and control of labour, labour camps , passes for transport, etc. It is most important that the Contractor, before tendering, shall obtain from the relevant Authority the fullest information regarding all such regulations and/or restrictions which may affect the information regarding all such regulations and/or restrictions which may affect the organisation of the works, supply and control of labour, etc., and allow accordingly in his tender.
No claim in respect of want of knowledge in this connection will be entertained.
H | SECURITY OF WORKS ETC.
The Contractor shall be entirely responsible for the security of all the works stores,materials, plant, personnel, etc., both his own and sub-contractors' and must provide all necessary watching, lighting and other precautions as necessary to ensure security against theft, loss or damage and the protection of the public.
I | PUBLIC AND PRIVATE ROADS.
Maintain as required throughout the execution of the works and make good any damage to public or private roads arising from or consequent upon the execution of the works to the satisfaction of the local and other competent authority and the Architect.
J | EXISTING PROPERTY.
The Contractor shall take every precaution to avoid damage to all existing property including roads, cables, drains and other services and he will be held responsible for and shall make good all such damage arising from the execution of this contract at his own expense to the satisfaction of the PROJECT
K | VISIT SITE AND EXAMINE DRAWINGS.
The Contractor is recommended to examine the drawings and visit the site the location of which is described in the Particular Preliminaries hereof. He shall be deemed to have acquainted himself therewith as to its nature, position, means of access or any other matter which, may affect his tender. No claim arising from his failure to comply with this recommendation will be considered.
L | ACCESS TO SITE AND TEMPORARY ROADS.
Means of access to the Site shall be agreed with the Architect prior to commencement of the work and Contractor must allow for building any necessary temporary access roads for the transport of the materials, plant and workmen as may be required for the complete execution of the works including the provision of temporary culverts, crossings, bridges, or any other means of gaining access to the Site. Upon completion of the works, the Contractor shall remove such temporary access roads; temporary culverts, bridges, etc., and make good and reinstate all works and surfaces disturbed to the satisfaction of the Architect.
M | AREA TO BE OCCUPIED BY THE CONTRACTOR
The area of the site which may be occupied by the Contractor for use of storage and for the purpose of erecting workshops, etc., shall be defined on site by the Architect.
N | OFFICE ETC. FOR THE CLIENT TEAM
The Contractor shall construct a temporary site office of type described and to the satisfaction of the Architect. He shall also provide a strong metal trunk complete with strong hasp and staple fastening and two keys. He shall maintain a lock-up type water or bucket closet for the sole use of the Architect and shall provide services of cleaner and pay all conservancy charges and keep both office and closet in a clean and sanitary condition from commencement to the completion of the works and dismantle and make good disturbed surfaces. The Contractor shall make available on the Site as and when required by the "Architect" a modern and accurate level together with levelling staff, ranging rods and 50 metre metallic or linen tape.
N | WATER AND ELECTRICITY SUPPLY FOR THE WORKS
The Contractor shall make arrangements to provide all necessary water, electric light and power required for use in the works. No guarantee is given or implied that sufficient water will be available from mains and the Contractor must make his own arrangements for augmenting this supply at his own cost. Nominated Sub--contractors are to be made liable for the cost of any water or electric current used and for any installation provided especially for their own use.
O | SANITATION OF THE WORKS
The Sanitation of the works shall be arranged and maintained by the Contractor to the satisfaction of the Government and/or Local Authorities, Labour Department and the Architect.
P | SUPERVISION AND WORKING HOURS
The works shall be executed under the direction and to the entire satisfaction in all respects of the Architect who shall at all times during normal working hours have access to the works and to the yards and workshops of the Contractor and sub-Contractors or other places where work is being prepared for the contract.
Q | PROVISIONAL SUMS.
The term "Provisional Sum" wherever used in these Bills of Quantities shall have the meaning stated in Section A item A7(i) of the Standard Method of Measurement.Such sums are net and no addition shall be made to them for profit.
R | PRIME COST (OR P.C.) SUMS.
The term "Prime Cost Sum" or "P.C. Sum" wherever used in these Bills of Quantities shall have the meaning stated in Section A item A7 (ii) of the Standard Method of Measurement . Persons or firms nominated by the Architect to execute work or to provide and fix materials or goods are described herein as Nominated Sub-Contractors.Persons or firms so nominated to supply goods or materials are described herein as Nominated Suppliers.
S | PROGRESS CHART.
The Contractor shall provide within two weeks of Possession of Site and in agreement with the Architect a Progress Chart for the whole of the works including the works of Nominated Sub-Contractors ; one copy to be handed to the Architect and a further copy to be retained on Site. Progress to be recorded and chart to be amended as necessary as the work
T | ADJUSTMENT OF P.C. SUMS.
In the final account all P.C. Sums shall be deducted and the amount properly expended upon the Architect'S order in respect of each of them added to the Contract sum. The Contractor shall produce to the Architect such quotations, invoices or bills, properly receipted, as may be necessary to show the actual details of the sums paid by the Contractor. Items of profit upon P.C. Sums shall be adjusted in the final account pro-rata to the amount paid. Items of "attendance" (as previously described) following P.C. Sums shall be adjusted pro-rata to the physical extent of the work executed (not pro-rata to the amount paid) and this shall apply even though the Contractor's priced Bill shows a percentage in the rate column in respect of them. Should the Contractor be permitted to tender and his tender be accepted of any work for which a P.C. Sum is included in these Bill of Quantities profit and attendance will be allowed at the same rate as it would be if the work were executed by a Nominated Sub-Contractor.
U | ADJUSTMENT OF PROVISIONAL SUMS.
In the final account all Provisional Sums shall be deducted and the value of the work properly executed in respect of them upon the Architect's order added to the Contract Sum. Such work shall be valued , but should any part of the work be executed by a Nominated Sub-Contractor, the value of such work or articles for the work to be supplied by a Nominated Supplier, the value of such work or articles shall be treated as a P.C. Sum and profit and attendance comparable to that contained in the priced Bills of Quantities for similar items added.
V | NOMINATED SUB-CONTRACTORS
When any work is ordered by the Architect to be executed by nominated sub-contractors, the Contractor shall enter into sub-contracts and shall thereafter be responsible for such sub-contractors in every respect. Unless otherwise described the Contractor is to provide for such Sub-Contractors any or all of the facilities described in these Preliminaries. The Contractor should price for these with the nominated Sub-contract Contractor's work concerned in the
P.C. Sums under the description "add for Attendance".
W | DIRECT CONTRACTS
Notwithstanding the foregoing conditions, the Government reserves the right to place a "Direct Contract" for any goods or services required in the works which are covered by a P.C. Sum in the Bills of Quantities and to pay for the same direct. In any such instances, profit relative to the P.C. Sum in the priced Bills of Quantities will be adjusted as described for P.C. Sums is allowed.
X | ATTENDANCE UPON OTHER TRADESMEN, ETC.
The Contractor shall allow for the attendance of trade upon trade and shall afford any tradesmen or other persons employed for the execution of any work not included in this Contract every facility for carrying out their work and also for use of his ordinary scaffolding. The Contractor, however, shall not be required to erect any special scaffolding for them. The Contractor shall perform such cutting away for and making good after the work of such tradesmen or persons as may be ordered by the Architect and the work will be measured and paid for to the extent executed at rates provided in these Bills.
Y | INSURANCE
The Contractor shall insure as required in Conditions No. 30 of the Conditions of Contract. No payment on account of the work executed will be made to the Contractor until he has satisfied the Architect either by production of an Insurance Policy or and Insurance Certificate that the provision of the foregoing Insurance Clauses have been complied with in all respects. Thereafter the Architect shall from time to time ascertain that premiums are duly paid up by the Contractor who shall if called upon to do so, produce the receipted premium renewals for the Architect's inspection.
Z | PROVISIONAL WORK
All work described as "Provisional" in these Bills of Quantities is subject to remeasurement in order to ascertain the actual quantity executed for which payment will be made. All "Provisional" and other work liable to adjustment under this Contract shall left uncovered for a reasonable time to allow all measurements needed for such adjustment to be taken by the Architect Immediately the work is ready for measuring, the Contractor shall give notice to the Architect. If the Contractor makes default in these respects he shall if the Architect so directs uncover the work to enable all measurements to be taken and afterwards reinstate at his own expense.
AA | ALTERATIONS TO BILLS, PRICING, ETC.
Any unauthorised alteration or qualification made to the text of the Bills of Quantities may cause the Tender to be disqualified and will in any case be ignored. The Contractor shall be deemed to have made allowance in his prices generally to cover any items against which no price has been inserted in the priced Bills of Quantities.All items of measured work shall be priced in detail and the Tenders containing Lump Sums to cover trades or groups of work must be broken down to show the price of each item before they will be accepted.
AB | BLASTING OPERATIONS
Blasting will only be allowed with the express permission of the Architect in writing. All blasting operations shall be carried out at the Contractor's sole risk and cost in accordance with any Government regulations in force for the time being, and any special regulations laid down by the Architect governing the use and storage of explosives.
AC | MATERIALS ARISING FROM EXCAVATIONS
Materials of any kind obtained from the excavations shall be the property of the Hospital. Unless the Architect directs otherwise such materials shall be dealt with as provided in the Contract. Such materials shall only be used in the works, in substitution of materials which the Contractor would otherwise have had to supply with the written permission of the Architect Should such permission be given, the Contractor shall make due allowance for the value of the materials so used at a price to be agreed.
AD | PROTECTION OF THE WORKS.
Provide protection of the whole of the works contained in the Bills of Quantities,including casing , casing up, covering or such other means as may be necessary to avoid damage to the satisfaction of the Architect and remove such protection when no longer required and make good any damage which may nevertheless have been done at completion free of cost to the Government.
| Total for general preliminaries carried to Summary | 0

## Demolitions
ITEM | DESCRIPTION | QTY | UNIT | RATE | AMOUNT
PROPOSED REFURBISHMENT AND EXTENSION OF OPERATING THEATRE
DEMOLITIONS
Demolition generally
The debris/waste arising from demolitions should be transported and disposed in a way to meet the guidelines of local authority, with the prior approval of Site Engineer. (Contractor is advised to visit the site to ascertain the extent of works before pricing)
The items for demolitions and removal shall include shoring making good disturbed areas to match existing and loading and carting away debris unless otherwise specified
To avoid disruption of the existing services by the Employer at the site, the Contractor shall in consultation with the Architect organize his works in a manner that the existing structures / services earmarked for demolitions but are under occupation by the Employer are demolished after the proposed (new) replacement structures / services are constructed and ready for occupation by the Employer. Unless otherwise unavoidable, the existing occupied structures / services must be demolished to pave way for the new structures, the Contractor shall at his own cost (except elsewhere allowed in the BOQ) provide a temporary measure subject to agreement with the Architect.
Doors
A | Carefully remove existing 900 x 2100mm high solid core flush doors faced both sides with 3mm thick ordinary veneer complete with frame including iron mongery and fixed to plastered and painted masonry wall and cart away | 6 | No |  | 0
Windows
B | Carefully demolish and remove existing 1500mm (average) high timber/steel windows glazed with glass louvres complete with and including 30mm round bars burglar proofing grilles fixed all round to plastered and painted masonry walling and cart away debris | 12 | Item |  | 0
C | Carefully demolish and remove existing weld mesh burglar proofing grilles fixed all round to plastered and painted masonry walling and cart away debris | 12 | Item |  | 0
SUPERSTRUCTURE WALLING
D | Carefully demolish existing 200mm thick solid concrete block/ natural stone/ masonry walling plastered and painted both sides and cart away debris | 129 | SM |  | 0
ROOFING
E | Caefully demolish the existing pitched roofing comprising corrugated iron sheets on timber purlins; timber trusses consisting of rafters ,ties, struts and ceiling joints; including all rainwater goods; fascia boards and eaves roof over hangs. | 408 | SM |  | 0
| FINISHES |  |  |  | 0
F | Carefully hack all the floor screed in readiness to receive polished terrazo and cart away debris as directed on site | 194 | SM |  | 0
|  |  | To Collection |  | 0
RELOCATING OF SERVICES
Relocating of waste water pipes and associated infrustucture
A | Relocate wastewater pipes from the working area including the manholes to an approved site in compliance with the hospital regulations; | 1 | Item |  | 0
B | Relocate Clean water pipes from the working area including the associated infrustructure i.e inspection manholes, air valves etc. to an approved site in compliance with the hospital regulations; | 1 | CM |  | 0
|  |  | To Collection |  | 0
Collection
| Page 01 |  |  |  | 0
| Page 02 |  |  |  | 0
| TOTAL CARRIED TO MAIN SUMMARY |  |  |  | 0

## Main Block
|  | Qnty | Unit | Rate | Amount
Substructure
SITE WORK
EXCAVATION
Excavating
Trenches to receive foundations; starting from existing ground level
A | generally | 45 | CM |  | 0
Pits to receive foundations; starting from existing ground level
B | generally | 26 | CM |  | 0
Disposal
Excavated material
C | backfilling into foundations; depositing and compacting in layers maximum 150 mm thick | 39 | CM |  | 0
Surplus excavated material
D | spread and levelling on site as directed | 32 | CM |  | 0
HARDCORE OR THE LIKE
Hardcore
Filling into excavations
E | generally; depositing and compacting in layers maximum 150 mm thick | 40 | CM |  | 0
Stone dust
Laying loose over hardcore base
F | 50 mm thick | 120 | SM |  | 0
ANTI-TERMITE TREATMENT
Premise 0.125% solution; applied by Insecta Ltd. or any equal and approved
At the rate of 5 litres per square metre
G | to hardcore beds and tops of foundation walls | 120 | SM |  | 0
|  |  |  | To Collection | 0
CONCRETE WORK
POURED CONCRETE
Plain
Normal; class 15; in
A | blinding; 50 mm thick | 6 | CM |  | 0
Reinforced
Normal; class 25; vibrated; in
B | foundations | 12 | CM |  | 0
C | ground beams | 7 | CM |  | 0
D | beds; 150 mm thick | 18 | CM |  | 0
E | columns | 1 | CM |  | 0
REINFORCEMENT
Bars; high yield steel; cold worked; B.S. 4461
In any location
F | 12 mm | 1313 | Kg |  | 0
G | 8 mm | 643 | Kg |  | 0
Fabric; B.S. 4483
Reference A142; weight 2.22 kgs per square metre
H | in any location | 120 | SM |  | 0
SHUTTERING
Generally
Generally to
J | foundations | 85 | SM |  | 0
K | sides of columns | 18 | SM |  | 0
L | edges; 75 to 150 mm wide | 79 | LM |  | 0
MASONRY
WALLS AND PIERS
Approved local stonework; roughly squared; bedding and jointing in cement mortar (1:4)
Walls
M | 200 mm thick | 117 | SM |  | 0
|  |  |  | To Collection | 0
THERMAL AND MOISTURE PROTECTION
COVERINGS AND LININGS
Bitumen paint
Generally; to concrete, masonry or screeded base; generally to
A | plinths | 24 | SM |  | 0
DAMP-PROOF COURSES
Polythene; 1000 gauge; 150 mm laps
Horizontal
B | generally | 120 | SM |  | 0
|  |  |  | To Collection | 0
Substructure
| Page No. 1 |  |  |  | 0
| Page No. 2 |  |  |  | 0
| Page No. 3 |  |  |  | 0
|  |  |  | To Summary | 0
Superstructure
CONCRETE WORK
POURED CONCRETE
Reinforced
Normal; class 25; vibrated; in
A | columns | 2 | CM |  | 0
B | beams | 13 | CM |  | 0
REINFORCEMENT
Bars; high yield steel; cold worked; B.S. 4461
In any location
C | 12 mm | 945 | Kg |  | 0
D | 8 mm | 558 | Kg |  | 0
SHUTTERING
Generally
Generally to
E | sides and soffits of beams | 177 | SM |  | 0
F | sides of columns | 41 | SM |  | 0
METALWORK
STRUCTURAL STEELWORK
Steel; B.S. 449 Part 2; bolted and welded site connections
Structural steelwork in
G | Z-purlins; 140 x 50 x 2.2 x 2 mm | 317 | Kg |  | 0
H | 50 x 50 x 3.5 mm SHS | 800 | Kg |  | 0
J | 75 x 75 x 3.5 mm SHS | 1890 | Kg |  | 0
Fittings
K | caps, brackets and the like |  | Item |  | 0
Fixings
L | bolts, distance pieces, rivets and the like |  | Item |  | 0
Two coats zinc chromate primer at works
M | generally |  | Item |  | 0
|  |  |  | To Collection | 0
Touching up priming coat; two undercoats; one coat oil paint full gloss finish
A | generally |  | Item |  | 0
WOODWORK
FINISHINGS AND FITTINGS
Softwood; grade GJ; pressure impregnated
Fascias and barge boards
B | 250 x 50 mm | 115 | LM |  | 0
THERMAL AND MOISTURE PROTECTION
COVERINGS AND LININGS
Galvanised steel; type LT5; as "Tekdek" or equal and approved; 26 gauge; pre-painted
Coverings; fixing to steel purlins at 1200 mm general spacing with galvanised steel hook bolts, nuts, neoprene washers and caps; 150 mm end laps and one and a half corrugation side laps
C | to sloping surfaces | 425 | SM |  | 0
FINISHES
DECORATIONS
One coat etching primer; two undercoats; one coat oil paint full gloss finish
Wood surfaces; on
D | fascia boards | 40 | SM |  | 0
One coat calcium plumbate primer; two undercoats; one coat oil paint gloss finish.
Iron or steel surfaces; on
E | gutters | 103 | SM |  | 0
F | large pipes | 0 | SM |  | 0
MECHANICAL ENGINEERING INSTALLATIONS
RAINWATER INSTALLATIONS
Gutterwork; 22 gauge galvanised mild steel box gutters and fittings; purpose made
Gutters; soldered joints in the running length; fixing with galvanised mild steel brackets at 900 mm centres
G | 300 x 300 mm | 57 | LM |  | 0
H | Fittings | 8 | No |  | 0
|  |  |  | To Collection | 0
Rainwater pipework; 22 gauge galvanised mild steel pipes and fittings; purpose made
Pipes; soldered connections in the running length; fixing with mild steel holderbats at 900 mm centres to backgrounds requiring plugging
A | 75 x 75 mm | 0 | LM |  | 0
B | Fittings | 0 | No |  | 0
|  |  |  | To Collection | 0
Superstructure
| Page No. 6 |  |  |  | 0
| Page No. 7 |  |  |  | 0
| Page No. 8 |  |  |  | 0
|  |  |  | To Summary | 0
Walling
CONCRETE WORK
CONCRETEWORK SUNDRIES
Wall ties; one end cast into concrete; other end built into joints of masonry
A | 25 x 450 mm | 272 | No |  | 0
MASONRY
WALLS AND PIERS
Approved local stonework; squared; medium chisel dressed both sides; bedding, jointing and recessed jointing both sides in cement mortar (1:4) as work proceeds
Walls
B | 100 mm thick; reinforced | 18 | SM |  | 0
C | 200 mm thick | 502 | SM |  | 0
THERMAL AND MOISTURE PROTECTION
DAMP-PROOF COURSES
B.S. 743 type A; bitumen hessian base
Horizontal
D | 100 mm wide | 7 | LM |  | 0
E | 200 mm wide | 179 | LM |  | 0
|  |  |  | To Summary | 0
Windows
CONCRETE WORK
PRECAST CONCRETE
Normal; class 25; vibrated; surface fair finish
Sills
A | 250 x 100 mm | 25 | LM |  | 0
DOORS AND WINDOWS
WINDOWS
Hardwood; grade F
Window boards
B | 250 x 25 mm; plugging | 25 | LM |  | 0
Powder coated aluminium windows; permanent ventilators full width; glazing beads and sealing strips; 6 mm laminated glass; supplied complete with necessary ironmongery
Fixing with aluminium screws; plugging; sealing with mastic; oiling and adjusting on completion
C | 600 x 600 mm | 8 | No |  | 0
D | 1200 x 600 mm | 2 | No |  | 0
E | 1500 x 1200 mm | 2 | No |  | 0
F | 1600 x 1200 mm | 1 | No |  | 0
G | 2000 x 1200 mm | 3 | No |  | 0
H | 2400 x 800 mm | 2 | No |  | 0
J | 2400 x 1200 mm | 1 | No |  | 0
|  |  |  | To Summary | 0
Doors
DOORS
Hardwood; grade F
Flush doors; solid core; 6 mm internal quality plywood facing both sides; hardwood lipping all edges
A | 800 x 2100 mm | 8 | No |  | 0
Flush doors; solid core; 6 mm internal quality plywood facing both sides; 200 x 200 mm high viewing panel; 15 x 15 mm hardwood glazing beads; hardwood lipping all edges
B | 900 x 2400 mm | 8 | No |  | 0
Panelled doors; 50 x 150 mm top and intermediate rails; 50 x 100 mm stiles; 50 x 200 mm bottom rails; two panels infilled with 20 mm thick blockboard panels with hardwood veneer.
C | 1300 x 2400 mm; in two leaves | 1 | No |  | 0
D | 1500 x 2400 mm; in two leaves | 5 | No |  | 0
E | 1800 x 2400 mm; in two leaves | 2 | No |  | 0
Frames
F | 200 x 50 mm; two labours; plugging | 141 | LM |  | 0
Beads and architraves
G | 25 x 50 mm | 282 | No |  | 0
IRONMONGERY
Supplying and fixing ironmongery; Dorma or equivalent
Fixing to concrete, masonry, metalwork or woodwork surfaces
H | butt hinges; 150 mm; steel | 48 | Prs |  | 0
J | bathroom dead lock | 8 | No |  | 0
K | mortice lock with cylindrical dead lock and set lever handles | 16 | No |  | 0
L | flush bolts; 150 mm | 8 | No |  | 0
M | disabled persons indicator plates | 2 | No |  | 0
N | push plates; 750 x 100 mm | 20 | No |  | 0
P | push plates; 900 x 100 mm | 24 | No |  | 0
Q | kick plates; 650 x 150 mm | 4 | No |  | 0
|  |  |  | To Collection | 0
A | kick plates; 750 x 150 mm | 20 | No |  | 0
B | kick plates; 800 x 150 mm | 16 | No |  | 0
C | kick plates; 900 x 150 mm | 24 | No |  | 0
D | overhead door closers; adjustable power; stainless steel cover | 16 | No |  | 0
|  |  |  | To Collection | 0
Doors
| Page No. 11 |  |  |  | 0
| Page No. 12 |  |  |  | 0
|  |  |  | To Summary | 0
Finishes
FINISHES
BACKGROUNDS
Mortar; cement and sand (1:4)
To floors; screeded
A | 25 mm thick; to receive terrazzo | 160 | SM |  | 0
B | 40 mm thick; to receive tiles | 45 | SM |  | 0
C | 20 mm thick; 100 mm wide; to receive terrazzo | 187 | LM |  | 0
To walls; screeded
D | 20 mm thick; to receive ceramic tiles | 219 | SM |  | 0
FINISHINGS
Render; cement and sand (1:4); wood floated
15 mm thick
E | to walls; externally | 223 | SM |  | 0
Plaster; 9 mm first coat of cement and sand (1:6); 3 mm second coat of cement and lime putty (1:10); steel trowelled
15 mm thick
F | to walls; internally | 583 | SM |  | 0
Terrazzo; first coat of cement and sand (1:3); second coat of coloured cement and local marble chippings (1:2); polished
25 mm thick
G | to floors | 160 | SM |  | 0
H | to skirtings; 100 mm wide | 187 | LM |  | 0
Granito tiles; polished; bedding and jointing in tile adhesive; grouting joints with matching coloured tile grout
300 x 300 x 10 mm
J | to floors | 45 | SM |  | 0
Ceramic tiles; P.C. Rate Shs 1500 per square metre, for supply, waste and delivery to site; bedding and jointing in approved tile adhesive; grouting joints with matching colour
600 x 300 x 8 mm
K | to walls | 219 | SM |  | 0
|  |  |  | To Collection | 0
SUSPENDED CEILINGS
Armstrong "Minaboard" accessible tile system suspended ceilings; 600 x 600 x 15 mm fissured mineral fibre tiles; complete with epoxy acrylic protected tee clips, pipped tabs, epoxy acrylic protected tee runners, hot dipped galvanised splice plates with edge trims; fixing with screws to backgrounds requiring plugging
Linings to form soffits; suspended on pre-straightened galvanised annealed iron wire hangers; fixing to screw eyes to backgrounds requiring plugging; generally to
A | ceilings | 159 | SM |  | 0
Armstrong "Minaboard" accessible tile system suspended ceilings; moisture resistant; 600 x 600 x 15 mm fissured mineral fibre tiles; complete with epoxy acrylic protected tee clips, pipped tabs, epoxy acrylic protected tee runners, hot dipped galvanised splice plates with edge trims; fixing with screws to backgrounds requiring plugging
Linings to form soffits; suspended on pre-straightened galvanised annealed iron wire hangers; fixing to screw eyes to backgrounds requiring plugging; generally to
B | ceilings | 46 | SM |  | 0
DECORATIONS
One mist coat and 2 finishing coats of External Quality Emulsion paint Color to approval. Range to be 1st quality paint from reputable manufacturer. Application to be in accordance with Manufacturer's specification.
Rendered surfaces; on
C | walls | 223 | SM |  | 0
One skim coat, three coats egg-shell emulsion paint; washable. Colour to approval. Range to be 1st quality paint. Application to be in accordance with Manufacturer's specification.
Plastered surfaces; on
D | walls | 583 | SM |  | 0
|  |  |  | To Collection | 0
Finishes
| Page No. 14 |  |  |  | 0
| Page No. 15 |  |  |  | 0
|  |  |  | To Summary | 0
Fittings
CONCRETE WORK
POURED CONCRETE
Reinforced
Normal; class 25; vibrated; in
A | worktops; 75 mm thick | 4 | SM |  | 0
REINFORCEMENT
Fabric; B.S. 4483
Reference A98; weight 1.54 kgs per square metre
B | in any location | 4 | SM |  | 0
SHUTTERING
Generally
Generally to
C | worktops | 4 | SM |  | 0
FINISHES
FINISHINGS
Granite; P.C. rate Shs. 12,000 per square metre; bedding and jointing in approved adhesive; grouting joints with matching coloured grout
20 mm thick
D | to worktops, vanity tops and the like | 5 | SM |  | 0
|  |  |  | To Summary | 0
Summary
| Substructure |  |  |  | 0
| Superstructure |  |  |  | 0
| Walling |  |  |  | 0
| Windows |  |  |  | 0
| Doors |  |  |  | 0
| Finishes |  |  |  | 0
| Fittings |  |  |  | 0
|  |  |  | To Summary | 0

## PC & PSS
Item | Description | Unit | Qnty | Amount
Work in this section shall be executed by approved Nominated Specialist Sub-Contractors. The Main Contractor shall be fully responsible for these Sub- Contractors in every respect.
1 | ELECTRICAL INSTALLATIONS
a | Provide Kshs.. 3,300,0000.00 being Prime Cost Sum for Electrical Installations | Item
b | Add for Profits | %
c | Add for General and Special Attendance | Item
2 | PLUMBING, DRAINANGE & SANITARYWARE
a | Provide Kshs.. 2,300,000 being the Prime Cost Sum for Plumbing, Drainage & Sanitaryware Installation | Item
b | Add for Profits | %
c | Add for General and Special Attendance | Item
3 | SWIMMING POOL PLANT
a | Provide Kshs.. 2,000,000 being the Prime Cost Sum for Supply and Installation of Fire fighting equipment | Item
b | Add for Profits | %
c | Add for General and Special Attendance | Item
4 | LANDSCAPING WORKS
a | Provide Kshs.. 300,000.00 being the Prime Cost Sum for Hot water Heating | Item
b | Add for Profits | %
c | Add for General and Special Attendance | Item
PROVISIONAL SUMS
The following Provisional Sums are to be measured on completion and priced in accordance with the rate contained in these Bills of Quantities or pro-rata thereto or deducted in whole if not required
Provisional Sum for
a | Allow a sum for opening up works and carrying out tests and Works Cube tests | Item
b | Allow a sum for external Works | Item
Total: To Main Summary

## MSS
PROPOSED REFURBISHMENT AND EXTENSION OF OPERATING THEATRE
KAKUMA
MAIN SUMMARY
BILL NO. |  |  | TOTAL
1 | PRELIMINARIES |  | 0
2 | DEMOLITIONS |  | 0
3 | MAIN BLOCK |  | 0
4 | PROVISIONAL AND PRIME COST SUMS |  | 0
5 | CONTINGENCY SUM |  | 0
| TOTAL CARRIED TO FORM OF TENDER (INCLUSIVE OF V.A.T.) | KSHS | 0
MAIN SUMMARY